## Sheet1
How are you proceeding? What are your impediments?
ACO SPRINT 1 November-December 2014
Daily Stand-up Meeting
Project Owner | S. Lewis
Project Members | See OWNER column
Committed Items (decided during sprint) | Project Plan Item # | Owner | Not Started | In Progress | Completed | State | Impediments | SIDEBAR
Create strategy and business plan for board/NAH | x | D.Coe |  | x
Determine core measures | x | K. Kauffman/D.Coe/B.Keeler |  | x
Spec and timeline for Cerner P1 build | x | D.Coe/K. Kauffman |  | x
Have 20 members in | x | S.Turner/L. Brugh |  | x
Community stakeholder engagement/BH | x | S.Turner |  | x
Map programs and metrics internal and external | x | K.Kauffman |  | x
Finalize NAQHC merger | x | M. Lewis |  | x
Data and data mgt. -sends to Cerner done | x | C. Currie/K.Kauffman/D.coe/B.Keeler |  | x
Employee communication on CM and DM | x | C. Currie/L.Brugh
Commence Monte Fiore, set scope | x | M.Carroll |  | x
Finance Charter/All charters | x | P.Langston/K.Kauffman |  | x
Also Attending | x | S.Mace